## Feature Stories
Feature ID | Area | Feature | User Story | Expected Behavior | Source Evidence | Test Method | Status | Last Tested | Test Result | Errors Found | Fix Status | Retest Result | Notes
TG-001 | Auth and configuration | Missing configuration screen | As a tenant admin, I want clear setup feedback when MSAL env vars are missing so I can configure the app before sign-in. | If any required env var is absent, the app renders Tenant Graph with a list of missing VITE_AAD_CLIENT_ID, VITE_AAD_TENANT_ID, or VITE_REDIRECT_URI and does not initialize MSAL. | src/App.tsx; src/auth/msal.ts; src/components/auth/SignInScreen.tsx | Targeted browser/static test | Verified | 2026-06-21 21:16 UTC | Missing config behavior is covered by missingRequiredEnvVars unit test and App source rendering MissingConfigScreen when hasMsalConfig is false. |  | No fix needed |  | Config calculation now has direct unit coverage.
TG-002 | Auth and configuration | Redirect origin normalization | As a user, I want localhost/127.0.0.1 mismatches normalized so MSAL redirect URI remains valid. | When current origin differs from VITE_REDIRECT_URI origin, main.tsx redirects to the configured origin preserving path, query, and hash. | src/main.tsx | Browser smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. localhost redirect normalized; popup returned to app workspace instead of nested prompt. |  | No fix needed |  | localhost redirect normalized; popup returned to app workspace instead of nested prompt.
TG-003 | Auth and configuration | Microsoft Entra sign-in popup | As a user, I want to sign in through Microsoft Entra ID so Tenant Graph can access delegated Graph data. | Unauthenticated users see a Sign in button; clicking it calls MSAL loginPopup with User.Read. | src/components/auth/SignInScreen.tsx; src/auth/msal.ts | Manual live auth test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Clicked Sign In in stale anonymous tab; MSAL popup opened and completed to authenticated workspace. |  | No fix needed |  | Clicked Sign In in stale anonymous tab; MSAL popup opened and completed to authenticated workspace.
TG-004 | Auth and configuration | Sign-in cancellation and error messaging | As a user, I want canceled sign-in to be quiet and real failures to be visible. | user_cancelled errors return silently; other login errors show an auth-error alert saying sign-in failed. | src/components/auth/SignInScreen.tsx | Targeted component test | Retested passed | 2026-06-21 20:55 UTC | Before fix: closing the MSAL popup returned to the sign-in screen with no alert. After fix: closing the popup shows a visible role=alert cancellation message. | ERR-004 | Fixed | Playwright retest passed: Sign-in was canceled. Use Sign in when you are ready. | Cancellation now gives concise retry-safe feedback and keeps Sign in available.
TG-005 | Auth and configuration | MSAL account activation | As a returning user, I want the existing account reused so I do not repeatedly sign in. | LOGIN_SUCCESS sets active account; on startup the first cached account becomes active when none is active. | src/main.tsx | Targeted integration test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Authenticated workspace shows active Break Glass account. |  | No fix needed |  | Authenticated workspace shows active Break Glass account.
TG-006 | Auth and configuration | Silent and incremental token acquisition | As a user, I want Graph permissions requested only when needed. | useGraphToken gets tokens silently for requested scopes and falls back to acquireTokenPopup only for interaction-required errors. | src/auth/useGraphToken.ts; src/auth/msal.ts | Targeted unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Live Graph calls loaded tenant overview and sign-in logs. |  | No fix needed |  | Live Graph calls loaded tenant overview and sign-in logs.
TG-007 | Auth and configuration | Sign out | As a signed-in user, I want to sign out from the account menu. | Account menu Sign out calls MSAL logoutRedirect. | src/components/layout/AppShell.tsx; src/components/layout/Toolbar.tsx | Manual live auth test | Verified | 2026-06-21 20:51 UTC | Live sign-out clicked account menu, redirected to Microsoft account picker, selected account, and returned Tenant Graph to its sign-in screen. Re-auth popup opened afterward. |  | No fix needed |  | Sign-out requires Microsoft account-picker confirmation, then returns to Tenant Graph sign-in screen.
TG-008 | Auth and configuration | Account menu external links | As a signed-in user, I want quick access to Microsoft profile and tenant switch pages. | Account menu opens profile and tenant switch URLs in new tabs with noopener/noreferrer. | src/components/layout/Toolbar.tsx | Targeted browser test | Verified | 2026-06-21 21:05 UTC | Account menu external links were intercepted with window.open: Profile opens myaccount.microsoft.com and Tenant switch opens /organizations. |  | No fix needed |  | Verified via window.open interception without leaving Tenant Graph.
TG-009 | Auth screen visual system | Vanta NET sign-in background | As a user, I want an Obsidian-like graph background on sign-in without interfering with controls. | Sign-in screen renders Vanta NET iframe/canvas background and keeps the sign-in panel usable. | src/components/auth/VantaNetBackground.tsx; src/styles/01-auth.css | Browser smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Sign-in screen retains Vanta NET background; previous smoke plus anonymous tab confirmed prompt. |  | No fix needed |  | Sign-in screen retains Vanta NET background; previous smoke plus anonymous tab confirmed prompt.
TG-010 | Workspace loading | Initial tenant overview load | As a signed-in admin, I want the workspace to load key Intune and Entra objects automatically. | Initial load queries /me, managed devices, mobile apps, compliance policies, device configs, settings catalog policies, enrollment profiles, assignment filters, and scope tags. | src/components/layout/useTenantGraphWorkspace.ts; src/graph/tenantGraphSources.ts | Live Graph/manual + adapter tests | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Live tenant overview loaded 176 objects and 96 relationships. |  | No fix needed |  | Live tenant overview loaded 176 objects and 96 relationships.
TG-011 | Workspace loading | Parallel Graph warning aggregation | As an admin, I want partial Graph failures visible without losing successful data. | Graph calls run with Promise.allSettled; fulfilled graphs merge, warnings collect, permission errors populate a banner. | src/graph/graphCalls.ts; src/components/layout/AppShell.tsx; src/components/layout/Sidebar.tsx | Static/unit review | Verified | 2026-06-21 21:12 UTC | Automated collectGraphs test verifies fulfilled graph data is preserved while warning and permission errors are aggregated. |  | No fix needed |  | Data-layer warning aggregation covered by graphCalls.test.ts.
TG-012 | Workspace loading | Loading state | As a user, I want visible feedback while tenant data loads. | Workspace starts with Loading tenant graph and displays a loading overlay while loading or expanding. | src/components/layout/useTenantGraphWorkspace.ts; src/components/layout/AppShell.tsx | Browser smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Reset flow showed loading while tenant graph reloaded. |  | No fix needed |  | Reset flow showed loading while tenant graph reloaded.
TG-013 | Workspace loading | Empty graph state | As a user, I want clear guidance when filters or search leave no graph data. | When not loading and visible graph has no nodes, main stage shows No graph data and suggests search/filter adjustment. | src/components/layout/AppShell.tsx | Targeted browser test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Disabling object types produced 0 objects, 0 relationships, and explicit no-visible-objects copy. |  | No fix needed |  | Disabling object types produced 0 objects, 0 relationships, and explicit no-visible-objects copy.
TG-014 | Workspace controls | Reset graph data | As an admin, I want to reload the tenant graph from Microsoft Graph. | Toolbar Reset calls loadGraph, clears transient search/path/limits, and reloads overview data. | src/components/layout/Toolbar.tsx; src/components/layout/useTenantGraphWorkspace.ts | Manual live auth test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Reset returned to 176 objects / 96 relationships after projected sign-in state. |  | No fix needed |  | Reset returned to 176 objects / 96 relationships after projected sign-in state.
TG-015 | Search | Toolbar search submit | As an admin, I want to search Intune and Entra objects from the toolbar. | Toolbar form prevents default submit and calls runSearch; blank searches are ignored. | src/components/layout/Toolbar.tsx; src/components/layout/useTenantGraphWorkspace.ts | Targeted component test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Toolbar search for iOS returned five relevant Intune objects. |  | No fix needed |  | Toolbar search for iOS returned five relevant Intune objects.
TG-016 | Search | Remote object search by visible type filters | As an admin, I want search to respect selected object type filters. | runSearch calls searchTenantObjects with enabled node types; source registry only runs matching search sources. | src/components/layout/useTenantGraphWorkspace.ts; src/graph/tenantGraphSources.ts | Adapter/unit tests | Retested passed | 2026-06-21 21:05 UTC | Remote search for iOS returns relevant Intune rows and now respects changed object-type filters after search. | ERR-005 | Fixed | Retest passed: all object types off gives 0 result rows and No matches. | Live search exercised through toolbar submit and visible-type filters.
TG-017 | Search | Local result fallback and no-query results | As an admin, I want already-loaded nodes searchable when no remote results are present. | Search results use remote results when available, otherwise local graph matches by label, subtitle, or type. | src/components/layout/useTenantGraphWorkspace.ts; src/utils/graphUtils.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Automated unit/type/build evidence. Unit coverage verifies local fallback/no-query result behavior. |  | No fix needed |  | Unit coverage verifies local fallback/no-query result behavior.
TG-018 | Search | Result ranking | As an admin, I want exact and relevant results surfaced first. | Results rank exact label, starts-with label, same selected type, and connected nodes before alphabetical tie-break. | src/components/layout/useTenantGraphWorkspace.ts | Targeted unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Top iOS results were exact/prefix matches before broader matches. |  | No fix needed |  | Top iOS results were exact/prefix matches before broader matches.
TG-019 | Search | Sidebar result paging | As an admin in a large tenant, I want results capped with an explicit load-more option. | Sidebar displays resultLimit rows, shows hidden count through button text, and Load more increases by 30. | src/components/layout/Sidebar.tsx; src/components/layout/useTenantGraphWorkspace.ts | Unit/static review | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Load 30 more increased result rows from 30 to 60. |  | No fix needed |  | Load 30 more increased result rows from 30 to 60.
TG-020 | Filtering | Object type filters | As an admin, I want to hide/show object families to reduce clutter. | Sidebar groups type checkboxes by zone; toggling updates typeFilter and graph nodes/edges are filtered accordingly. | src/components/layout/Sidebar.tsx; src/utils/graphUtils.ts; src/utils/graphZones.ts | Unit test | Retested passed | 2026-06-21 21:05 UTC | Object type filters now filter both graph objects and existing remote search results. Turning all object types off shows 0 objects, 0 relationships, and No matches. | ERR-005 | Fixed | Retest passed in live browser after reload. | Object type filters can drive graph to explicit empty state and restore.
TG-021 | Filtering | Relationship type filters | As an admin, I want to hide/show relationship types to reduce clutter. | Relationship checkboxes are generated from tenantRelationshipTypes; disabled relationships are removed from visible graph. | src/components/layout/Sidebar.tsx; src/utils/graphUtils.ts | Unit test | Verified | 2026-06-21 21:05 UTC | Relationship type filter verified live: disabling Scope tag reduced visible relationships from 96 to 2 and restoring the checkbox restored the relationship set. |  | No fix needed |  | Relationship filter behavior verified in browser.
TG-022 | Filtering | Graph object display limit | As an admin in a large tenant, I want graph rendering capped by default with explicit load more. | Visible graph is capped at 180 nodes, selected context is prioritized, and Load more increases by 180. | src/components/layout/useTenantGraphWorkspace.ts; src/utils/graphUtils.ts; src/components/layout/AppShell.tsx | Unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Default graph cap is active; overview remains bounded and paged. |  | No fix needed |  | Default graph cap is active; overview remains bounded and paged.
TG-023 | Graph rendering | Three.js scene lifecycle | As a user, I want the graph to render smoothly without leaking WebGL resources. | Canvas initializes scene/camera/renderer/OrbitControls and disposes controls, objects, renderer, listeners, resize observer, and animation frame on unmount. | src/components/graph/TenantGraphCanvas.tsx; src/components/graph/threeGraphObjects.ts | Static review + browser smoke | Verified | 2026-06-21 21:16 UTC | Three.js scene lifecycle is covered by source cleanup inspection and sign-out/unmount browser evidence: app returns to sign-in screen with no graph canvas. Cleanup removes listeners, controls, disposed objects, renderer, and canvas. |  | No fix needed |  | Lifecycle cleanup source and sign-out unmount behavior verified.
TG-024 | Graph rendering | Node icons by object type and device platform | As a non-admin viewer, I want nodes to visually communicate what kind of object they represent. | Renderer uses typed glyphs for users, devices, groups, roles, apps, policies, filters, scope tags, sign-ins, locations, and OS/device distinctions. | src/components/graph/nodeIcons.ts; src/components/graph/TenantGraphCanvas.tsx | Browser/canvas smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Desktop screenshot shows typed icons and OS/type legend. |  | No fix needed |  | Desktop screenshot shows typed icons and OS/type legend.
TG-025 | Graph rendering | App icons and user profile images | As a viewer, I want real app/user images when Graph provides them and safe fallbacks otherwise. | Media hydration fetches up to 24 app icons and 32 user photos, ignores failures, and node sprites use images when available. | src/graph/mediaEnrichment.ts; src/components/graph/useNodeImageCache.ts; src/components/graph/nodeIcons.ts | Unit tests | Verified | 2026-06-21 21:13 UTC | App icon hydration, user photo hydration, photo cap, and missing-photo fallback are covered by regression tests; live Graph 404 is documented as non-blocking ERR-001. | ERR-001 | No fix needed |  | Expected missing profile-photo 404 does not block graph load and falls back to glyph.
TG-026 | Graph rendering | Semantic cluster zones | As a viewer, I want object types clustered by meaning. | layoutGraph groups nodes into people, devices, groups, apps, policies, access, guardrails, and context zones with rendered semantic boundaries. | src/components/graph/graphLayout.ts; src/utils/graphZones.ts; src/components/graph/threeGraphObjects.ts | Static/browser test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Desktop screenshot shows semantic cluster zones and labels. |  | No fix needed |  | Desktop screenshot shows semantic cluster zones and labels.
TG-027 | Graph rendering | Central and selected node prominence | As a viewer, I want the selected object to be visually dominant. | Central/selected nodes get larger icon size, halo, focus rings, higher render order, and selected label priority. | src/components/graph/TenantGraphCanvas.tsx; src/components/graph/graphVisualPolicy.ts | Browser/canvas smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Selected Break Glass node renders with dominant halo and label. |  | No fix needed |  | Selected Break Glass node renders with dominant halo and label.
TG-028 | Graph rendering | Relationship styling and direction | As a viewer, I want edge style to communicate relationship meaning. | Assignments, membership, primary user, filters, scope tags, detected apps, and CA edges use distinct opacity/dashes/double lines/arrows/pulses. | src/components/graph/graphVisualPolicy.ts; src/components/graph/TenantGraphCanvas.tsx | Static/browser test | Verified | 2026-06-21 21:16 UTC | Relationship visual policy tests cover assignment, membership dashed, primary-user double-line, filtered-by dotted, detected-app animated, scope-tag thin styles, and direction endpoints. |  | No fix needed |  | Visual line style and direction behavior covered by graphVisualPolicy tests plus live edge click.
TG-029 | Graph rendering | Focus depth dimming | As a viewer, I want to focus on direct or two-hop relationships. | Toolbar Focus 0/1/2 controls focusTenantGraph and canvas opacity tiers for selected relationships. | src/components/layout/Toolbar.tsx; src/components/layout/useTenantGraphWorkspace.ts; src/components/graph/graphVisualPolicy.ts | Unit/static review | Verified | 2026-06-21 21:06 UTC | Focus depth controls verified live: Direct value 1, Two-Hop value 2, and Off value 0 all apply and reset without breaking the graph. |  | No fix needed |  | Visual dimming policy remains source-covered; control behavior verified in browser.
TG-030 | Graph rendering | Zoom, pan, and rotate | As a graph user, I want to navigate the graph spatially. | OrbitControls enable damping, screen-space panning, min/max distance, and canvas cursor states. | src/components/graph/TenantGraphCanvas.tsx | Browser interaction test | Verified | 2026-06-21 21:06 UTC | Zoom/pan/rotate gestures were exercised on the Three.js canvas, then Fit restored a usable graph viewport. |  | No fix needed |  | Wheel, drag, shifted drag, and Fit all left canvas visible and stable.
TG-031 | Graph rendering | Hover tooltip | As a viewer, I want lightweight metadata on hover. | Pointer raycast detects nodes, edges, and zones; hover tooltip shows readable object/relationship/cluster copy. | src/components/graph/TenantGraphCanvas.tsx; src/components/graph/graphHoverCopy.ts | Browser interaction test | Verified | 2026-06-21 20:51 UTC | Coordinate sweep found node tooltip for an assignment filter; tooltip showed label, type, relationship count, and metadata. |  | No fix needed |  | Graph hover verified by pointer sweep around rendered canvas nodes.
TG-032 | Graph rendering | Node click selection and expansion | As an admin, I want clicking a node to select it and progressively load related data. | Canvas node click selects node; workspace selectNode dispatches selection and calls expandNode when expandable. | src/components/graph/TenantGraphCanvas.tsx; src/components/layout/useTenantGraphWorkspace.ts; src/graph/tenantGraphExpansion.ts | Live/manual + unit tests | Verified | 2026-06-21 21:06 UTC | Direct graph-node click verified from a tooltip-discovered canvas coordinate; clicked settings catalog policy pinned matching details. |  | No fix needed |  | Node selection and expansion state verified directly on the Three.js canvas.
TG-033 | Graph rendering | Edge click selection | As a viewer, I want to inspect a relationship by clicking an edge. | Canvas edge click dispatches selectedEdgeId and opens relationship inspector. | src/components/graph/TenantGraphCanvas.tsx; src/components/layout/useTenantGraphWorkspace.ts | Browser interaction test | Verified | 2026-06-21 20:51 UTC | Canvas edge click selected a Scope tag relationship and opened the inspector breadcrumb/relationship detail. |  | No fix needed |  | Edge click verified at canvas coordinate identified from tooltip sweep.
TG-034 | Graph rendering | Cluster click isolate and zoom | As a viewer, I want to click a cluster to isolate related object types. | Zone click fits camera to zone and updates typeFilter to that zone object set while closing inspector. | src/components/graph/TenantGraphCanvas.tsx; src/components/layout/useTenantGraphWorkspace.ts; src/utils/graphZones.ts | Browser interaction test | Verified | 2026-06-21 20:51 UTC | Canvas cluster click isolated policy object types and zoomed to 113 policy objects / 0 relationships. |  | No fix needed |  | Cluster click verified for Policies zone; filters restored afterward.
TG-035 | Graph rendering | Fit and reset view | As a graph user, I want quick camera controls. | Toolbar Fit calls canvas fitView using current positions; View resets camera to default position/target. | src/components/layout/Toolbar.tsx; src/components/graph/TenantGraphCanvas.tsx; src/components/graph/graphCamera.ts | Browser interaction test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Fit and View controls stayed clickable and preserved canvas. |  | No fix needed |  | Fit and View controls stayed clickable and preserved canvas.
TG-036 | Graph rendering | Progressive labels and collision handling | As a viewer, I want labels without excessive clutter. | Labels show by zoom, selected, hovered, direct relation, and priority; overlapping lower-priority labels fade or hide. | src/components/graph/graphLabelVisibility.ts | Static/browser test | Verified | 2026-06-21 21:16 UTC | Progressive label priority and collision behavior are covered by graphVisualPolicy label-priority tests, graphLabelVisibility collision tests, and live screenshots/label visibility evidence. |  | No fix needed |  | Collision helper and priority policy now have unit coverage.
TG-037 | Graph overlays | Legend | As a viewer, I want a legend for node colors and icons. | Graph overlays show legend entries for Windows, iOS, users, roles, apps, policies, filters, scope tags, and groups. | src/components/graph/GraphOverlays.tsx | Browser smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Legend visible with Windows, iOS, Users, Roles, Apps, Policies, Filters, Scope tags, Groups. |  | No fix needed |  | Legend visible with Windows, iOS, Users, Roles, Apps, Policies, Filters, Scope tags, Groups.
TG-038 | Graph overlays | Mini map | As a viewer, I want an overview of graph density and selected object location. | Mini map renders up to 260 node points, zone bands, a viewport marker, node count, and selected-node ring. | src/components/graph/GraphOverlays.tsx | Browser smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Mini map visible with selected marker and count. |  | No fix needed |  | Mini map visible with selected marker and count.
TG-039 | Selection details | No selection state | As a user, I want guidance when no object is selected. | Details panel shows Selection and Select an object to explain it when node is absent. | src/components/details/DetailsPanel.tsx | Targeted component test | Verified | 2026-06-21 21:16 UTC | No-selection state is covered by DetailsPanel server-render test, which verifies the Selection panel renders Select an object to explain it when no node is selected. |  | No fix needed |  | Live tenant auto-selects after load; source state now has direct render coverage.
TG-040 | Selection details | Selected object metadata | As a user, I want selected object details pinned in the sidebar. | Details panel shows node label, subtitle/type, metadata rows, and impact metrics for the selected node. | src/components/details/DetailsPanel.tsx; src/utils/graphUtils.ts | Unit/static review | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Selected object details panel and inspector show Break Glass metadata. |  | No fix needed |  | Selected object details panel and inspector show Break Glass metadata.
TG-041 | Selection details | Expand action state | As an admin, I want Expand to tell me when more relationships are unavailable. | Expand is disabled for unsupported, virtual, busy, or already-expanded states and shows specific helper text. | src/components/details/DetailsPanel.tsx; src/utils/graphUtils.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Expanded/no-expansion states are visible and disabled when no action is available. |  | No fix needed |  | Expanded/no-expansion states are visible and disabled when no action is available.
TG-042 | Readable mode | Friendly summaries | As a non-admin viewer, I want plain-English explanations of objects. | Friendly Names mode shows object type, summary, impact, next step, badges, and glossary definitions. | src/components/details/DetailsPanel.tsx; src/utils/readableGraph.ts; src/utils/readableNodeConfig.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Friendly summaries visible for user, assignment filter, and sign-in event objects. |  | No fix needed |  | Friendly summaries visible for user, assignment filter, and sign-in event objects.
TG-043 | Readable mode | Technical details disclosure | As a non-admin viewer, I want technical fields available without clutter. | Friendly Names mode hides metadata in a collapsed Technical details disclosure; Admin mode shows metadata directly. | src/components/details/DetailsPanel.tsx | Browser/component test | Verified | 2026-06-21 21:05 UTC | Friendly Names technical-details disclosure opened from collapsed state and showed Type/upn metadata, then closed cleanly. |  | No fix needed |  | Details disclosure interaction verified in browser.
TG-044 | Readable mode | At-a-glance cluster summaries | As a non-admin viewer, I want a quick summary of visible object groups. | Friendly Names mode shows cluster summaries with counts, descriptions, and platform/policy details. | src/components/details/ClusterSummary.tsx; src/utils/readableGraph.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. At-a-glance cluster summary visible and readable. |  | No fix needed |  | At-a-glance cluster summary visible and readable.
TG-045 | Readable mode | Data confidence signals | As a viewer, I want to know when data may be incomplete. | Friendly Names mode shows Missing permission or Partial data badges when permissionError or warnings exist. | src/components/layout/Sidebar.tsx | Targeted component test | Verified | 2026-06-21 21:12 UTC | Data confidence signals are driven by permissionError/warnings; collectGraphs test verifies permissionError propagation and Sidebar source renders Missing permission/Partial data badges. |  | No fix needed |  | Forced warning state covered by unit test plus source evidence.
TG-046 | Readable mode | Why does this apply path finder | As a non-admin viewer, I want a path explanation between selected object and a relevant target. | Path finder lists target candidates, produces shortest-path steps, and tells user to expand/increase depth when no path exists. | src/components/details/PathFinder.tsx; src/utils/readableGraph.ts | Unit test | Verified | 2026-06-21 21:12 UTC | Readable path finder positive path is covered by existing explainReadablePath/readablePathCandidates tests, and live UI showed explicit partial-data state. |  | No fix needed |  | Positive path behavior covered in graphUtils/readableGraph tests.
TG-047 | Admin mode | Evidence drawer | As an admin, I want raw normalized and Graph evidence for verification. | Admin mode renders a collapsed Evidence drawer with grouped normalized/metadata/raw fields, loaded relationships, and raw JSON. | src/components/details/EvidenceDrawer.tsx; src/utils/evidence.ts | Unit test | Verified | 2026-06-21 21:05 UTC | Admin mode renders Evidence drawer with normalized, metadata, and raw Graph fields for the selected object. |  | No fix needed |  | Evidence drawer verified in browser Admin mode.
TG-048 | Relationship inspector | Inspector open and close | As a viewer, I want a right inspector for selected nodes or relationships. | Inspector opens for selected node/edge and close clears selected edge/inspector state. | src/components/graph/RelationshipInspector.tsx; src/components/layout/useTenantGraphWorkspace.ts | Browser interaction test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Right-side inspector is visible and close/copy controls are exposed. |  | No fix needed |  | Right-side inspector is visible and close/copy controls are exposed.
TG-049 | Relationship inspector | Relationship breadcrumb | As a viewer, I want relationship context between source and target. | When an edge is selected, inspector shows source button, readable relationship label/sentence, and target button. | src/components/graph/RelationshipInspector.tsx | Browser interaction test | Verified | 2026-06-21 21:05 UTC | Edge click opened the relationship inspector with breadcrumb source, relationship label, and target object copy. |  | No fix needed |  | Breadcrumb verified during edge-click test.
TG-050 | Relationship inspector | Copy actions | As an admin, I want to copy name, object ID, and Graph query quickly. | Inspector action buttons write label, nodeApiId, or graphQueryForNode to clipboard, with textarea fallback. | src/components/graph/RelationshipInspector.tsx | Browser interaction test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Copy name action clicked without page error; copy/link buttons visible. |  | No fix needed |  | Copy name action clicked without page error; copy/link buttons visible.
TG-051 | Relationship inspector | Admin center links | As an admin, I want fast navigation to Intune and Entra. | Inspector Intune and Entra buttons open admin center roots in new tabs for selected object. | src/components/graph/RelationshipInspector.tsx | Browser interaction test | Verified | 2026-06-21 21:05 UTC | Intune and Entra inspector buttons were intercepted with window.open and produced admin-center URLs. |  | No fix needed |  | Admin center link behavior verified without opening external tabs.
TG-052 | Relationship inspector | Relationship lists and subsections | As a viewer, I want relationships grouped into usable lists. | Inspector lists up to 10 visible relationships, plus assignment, filter, and scope tag subsections with empty states. | src/components/graph/RelationshipInspector.tsx | Targeted component test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Relationships, assignments, filters, scope tags, and sign-ins sections render in inspector. |  | No fix needed |  | Relationships, assignments, filters, scope tags, and sign-ins sections render in inspector.
TG-053 | Relationship inspector | Raw Graph IDs | As an admin, I want stable IDs for correlation and verification. | Inspector shows Tenant Graph ID, Graph object ID, edge ID, source, and target in technical rows. | src/components/graph/RelationshipInspector.tsx | Targeted component test | Verified | 2026-06-21 21:05 UTC | Relationship inspector exposes Raw Graph IDs, Copy ID, and Graph query actions for the selected object. |  | No fix needed |  | Raw ID surface verified in browser.
TG-054 | Sign-in investigation | Sign-ins panel availability | As an admin, I want sign-in logs only where relevant. | Sign-ins panel supports users, devices, apps, network locations, and sign-in events; other nodes show explanatory empty text. | src/components/details/SignInInvestigation.tsx; src/components/details/useSignInInvestigation.ts | Targeted component test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Sign-ins panel appears for selected user. |  | No fix needed |  | Sign-ins panel appears for selected user.
TG-055 | Sign-in investigation | Sign-in filters and bounded query | As an admin, I want to filter sign-ins by time range, result, and Conditional Access status. | Load builds /auditLogs/signIns query with range clamped to 1-30 days, top 5-50, optional context and CA status filters, then client-filters result and CA states. | src/components/details/SignInInvestigation.tsx; src/graph/signInLogQuery.ts | Unit tests | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Range, CA, result filters and bounded load button are visible and functional. |  | No fix needed |  | Range, CA, result filters and bounded load button are visible and functional.
TG-056 | Sign-in investigation | Incremental CA details scope | As an admin, I want policy names requested only when enabled. | When Request CA policy names and controls is checked, loadSignInLogs requests AuditLog.Read.All plus Policy.Read.ConditionalAccess; otherwise AuditLog.Read.All only. | src/components/details/SignInInvestigation.tsx; src/graph/signInLogs.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. CA details scope path returned report-only Conditional Access policy counts. |  | No fix needed |  | CA details scope path returned report-only Conditional Access policy counts.
TG-057 | Sign-in investigation | Sign-in load more | As an admin, I want to page through more sign-ins. | When Graph returns nextLink, Load more sign-ins appends events and preserves selected event when possible. | src/components/details/useSignInInvestigation.ts; src/components/details/SignInInvestigation.tsx | Targeted unit/component test | Verified | 2026-06-21 21:12 UTC | Sign-in load-more adapter now has explicit nextLink coverage: loadSignInLogs uses the provided Microsoft Graph nextLink and returns the next page token. |  | No fix needed |  | Load-more data path covered by signInLogs.test.ts.
TG-058 | Sign-in investigation | Access decision summary | As an admin, I want quick status of Conditional Access impact. | Loaded events show access decision strip plus metrics for total events, failures, CA failed, and report-only counts. | src/components/details/SignInInvestigation.tsx | Targeted component test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Sign-in summary showed Success and Report-only impact counts. |  | No fix needed |  | Sign-in summary showed Success and Report-only impact counts.
TG-059 | Sign-in investigation | Sign-in detail view | As an admin, I want event details to troubleshoot access. | Selected event shows user, app, resource, failure reason, client, device, location, risk, correlation ID, CA policy groups, and Entra sign-in link. | src/components/details/SignInInvestigation.tsx | Targeted component test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Clicking a sign-in event opened detailed sign-in fields. |  | No fix needed |  | Clicking a sign-in event opened detailed sign-in fields.
TG-060 | Sign-in investigation | Missing sign-in/CA permission states | As an admin, I want clear missing permission guidance. | 401/403 sign-in errors mention AuditLog.Read.All and required roles; missing CA policy detail warns about Policy.Read.ConditionalAccess and roles. | src/components/details/useSignInInvestigation.ts; src/components/details/SignInInvestigation.tsx | Targeted unit/component test | Verified | 2026-06-21 21:13 UTC | Missing sign-in/CA permission copy is covered by a forced GraphError(403) regression test and source-rendered warning state. |  | No fix needed |  | useSignInInvestigation.test.ts covers missing AuditLog.Read.All / Reports Reader / Policy.Read.ConditionalAccess guidance.
TG-061 | Sign-in investigation | Project sign-in onto graph | As an admin, I want a sign-in event visualized in context. | Show on graph projects sign-in event, user, resource app, location, and CA policies into graph and selects the sign-in event node. | src/components/details/SignInInvestigation.tsx; src/graph/signInEventGraph.ts; src/components/layout/useTenantGraphWorkspace.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Projecting a sign-in event increased graph objects from 177 to 180, then reset removed it. |  | No fix needed |  | Projecting a sign-in event increased graph objects from 177 to 180, then reset removed it.
TG-062 | Microsoft Graph data | Normalized tenant graph model | As a developer/admin, I want all Graph data normalized before rendering. | TenantGraph uses typed TenantNode and TenantEdge arrays with typed node and relationship kinds. | src/models/tenantGraph.ts | Typecheck/static review | Verified | 2026-06-21 20:47 UTC | Automated unit/type/build evidence. Typecheck/tests verify normalized TenantGraph/TenantNode/TenantEdge contracts. |  | No fix needed |  | Typecheck/tests verify normalized TenantGraph/TenantNode/TenantEdge contracts.
TG-063 | Microsoft Graph data | Object adapters | As a developer/admin, I want Graph responses converted into consistent labels, subtitles, metadata, raw evidence, and IDs. | Adapters normalize users, groups, directory roles, managed devices, mobile apps, detected apps, policies, assignment filters, scope tags, assignments, and directory objects. | src/graph/adapters.ts | Unit tests/static review | Verified | 2026-06-21 20:47 UTC | Automated unit/type/build evidence. Adapter tests verify Graph response normalization paths. |  | No fix needed |  | Adapter tests verify Graph response normalization paths.
TG-064 | Microsoft Graph data | Directory role display-name hydration | As an admin, I want directory roles to show names instead of raw IDs. | User memberOf directoryRole nodes hydrate missing names from /directoryRoles?$select=id,displayName,description,roleTemplateId. | src/graph/tenantGraphExpansion.ts; src/graph/tenantGraphSources.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Automated unit/type/build evidence. Directory role hydration tests verify display names instead of GUID labels. |  | No fix needed |  | Directory role hydration tests verify display names instead of GUID labels.
TG-065 | Microsoft Graph data | Safe mobile app queries and fallback | As an admin, I want mobile app search/overview to work even when selected fields are rejected. | Mobile app collections avoid largeIcon; 400 on selected collection query retries without $select. | src/graph/tenantGraphSources.ts; src/graph/mediaEnrichment.ts | Unit tests | Verified | 2026-06-21 20:47 UTC | Automated unit/type/build evidence. Mobile app query fallback tests verify safe collection queries. |  | No fix needed |  | Mobile app query fallback tests verify safe collection queries.
TG-066 | Microsoft Graph data | Broad assignment virtual targets | As an admin, I want All users/devices shown without invalid group expansion. | Assignment targets for all devices/users become virtual group nodes and are non-expandable. | src/graph/adapters.ts; src/utils/graphUtils.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Automated unit/type/build evidence. Broad assignment virtual-target tests prevent invalid expansion warnings. |  | No fix needed |  | Broad assignment virtual-target tests prevent invalid expansion warnings.
TG-067 | Microsoft Graph data | Progressive expansion by node type | As an admin, I want expansion to load only useful relationship types by depth. | Devices expand users/detected apps; users expand memberOf/devices; groups and roles expand members; apps/policies/enrollment expand assignments; depth fanout is capped. | src/graph/tenantGraphExpansion.ts | Unit/live test | Verified | 2026-06-21 21:05 UTC | Progressive expansion state verified on a settings catalog policy: selected policy showed disabled Expanded depth 1 with guidance to increase relationship depth. |  | No fix needed |  | Live policy selection plus unit expansion-state coverage verify terminal/depth behavior.
TG-068 | Microsoft Graph data | Conditional Access classifier | As an admin, I want CA results classified in plain operational categories. | Classifier distinguishes applied, failed, not applied, report-only, unknown, and missing details with policy groupings and tones. | src/graph/conditionalAccessEvaluation.ts | Unit test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Live CA classifier surfaced report-only impact; unit coverage also exercises classifier states. |  | No fix needed |  | Live CA classifier surfaced report-only impact; unit coverage also exercises classifier states.
TG-069 | States and errors | Permission banners and warnings | As an admin, I want Graph permission problems exposed without blocking all data. | PermissionError shows banner; sidebar data confidence and warnings list show partial data. | src/components/layout/AppShell.tsx; src/components/layout/Sidebar.tsx; src/graph/graphCalls.ts | Targeted component/unit test | Verified | 2026-06-21 21:12 UTC | Permission banners and graph warnings are backed by collectGraphs warning/permissionError propagation and AppShell/Sidebar source rendering. |  | No fix needed |  | Forced warning state covered by unit test plus UI source evidence.
TG-070 | Responsive UX | Desktop-first responsive layout | As an admin, I want the app usable on desktop and not broken on mobile widths. | CSS uses responsive workspace layout, capped canvas heights, and adjusted panels for small screens. | src/styles/07-responsive.css; src/styles/*.css | Browser responsive smoke | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Mobile smoke had no horizontal overflow; toolbar, graph, legend, minimap fit 390px width. |  | No fix needed |  | Mobile smoke had no horizontal overflow; toolbar, graph, legend, minimap fit 390px width.
TG-071 | Accessibility | Keyboard and ARIA affordances | As a user, I want controls discoverable by assistive tech and keyboard. | Toolbar search has aria-label, graph controls use labels, inspector/mini map/sign-in sections use aria labels, buttons are native. | src/components/**/*.tsx | Accessibility snapshot/manual keyboard test | Verified | 2026-06-21 21:05 UTC | Keyboard tour verified: fresh Tab order starts at search, reaches toolbar controls/account/results, Enter submits search, Tab reaches a result, and Enter pins details. |  | No fix needed |  | Keyboard-only search and result selection verified in browser.
TG-072 | Accessibility | Reduced motion support | As a motion-sensitive user, I want animation reduced when requested. | CSS includes reduced-motion fallback for transitions/animations. | src/styles/00-base.css; src/styles/*.css | Static/browser media test | Verified | 2026-06-21 20:47 UTC | Browser/live tenant pass. Reduced-motion source scan confirms centralized prefers-reduced-motion fallback. |  | No fix needed |  | Reduced-motion source scan confirms centralized prefers-reduced-motion fallback.
TG-073 | Sign-in investigation | Conditional Access failure projection focus | As Jorge Suarez, I want a failed sign-in that I choose to stay selected when I show it on the graph, so I can inspect the failure instead of being moved back to a successful login. | After a successful sign-in projection already exists, projecting a failed sign-in creates/updates the failed sign-in node and sets selectedNodeId and centralNodeId to signInEvent:<clicked event id>. Older sign-in projections may remain visible but must not steal focus. | src/components/layout/useTenantGraphWorkspace.ts; src/components/layout/useTenantGraphWorkspace.test.ts; src/graph/signInEventGraph.ts | Targeted reducer regression test | Retested passed | 2026-06-21 23:48 UTC | Regression creates a prior successful Azure Portal sign-in for Jorge Suarez, then projects a failed 53003 event. The workspace selects and centers signInEvent:failure-1. | ERR-006 | Fixed | Vitest targeted regression passed. | Covers the reported workflow where viewing failures in the graph defaulted to a successful login attempt.
TG-074 | Sign-in investigation | Projected sign-in keeps user investigation context | As Jorge Suarez, I want the Sign-ins panel to continue investigating my sign-ins after I project one event, so switching from successful events to failed events does not silently narrow to the old success event. | A projected sign-in node carries userId, userPrincipalName, and userDisplayName metadata. When it is selected, Sign-ins loads related events for that user and still honors CA/result filters. | src/graph/signInEventGraph.ts; src/graph/signInLogQuery.ts; src/components/details/SignInInvestigation.tsx; src/graph/signInLogs.test.ts | Unit regression plus live browser retest | Retested passed | 2026-06-21 23:48 UTC | After projecting a successful Tenant Graph sign-in for Jorge Suarez, CA Failed + Result Failure returned 5 failed events and projecting one selected Failure / Tenant Graph. | ERR-007 | Fixed | Vitest and Playwright retest passed. | Prevents the Sign-ins panel from becoming trapped on the previously projected successful event.
TG-075 | Sample tenant | Sample tenant entry point | As a prospective user, I want to open a realistic sample tenant without Entra sign-in so I can evaluate Tenant Graph safely. | The sign-in and missing-config screens expose a Sample tenant button. Clicking it enables sample mode and renders the normal workspace with account name Sample tenant / Contoso, backed by the sample Graph client instead of MSAL. | src/App.tsx; src/components/auth/SignInScreen.tsx; src/demo/sampleTenantClient.ts | Browser sample entry test | Verified | 2026-06-23 17:51 UTC | Browser sample entry: sign-in screen Sample tenant button opened shared workspace at ?sampleTenant=1 with Sample tenant / Contoso and zero console errors. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-076 | Sample tenant | Direct sample tenant URL and exit | As a reviewer, I want a shareable sample URL and a clean exit path so I can demo the app and return to real sign-in. | Loading ?sampleTenant=1 opens the sample workspace directly. Exiting sample mode removes the query parameter and returns to the unauthenticated or missing-config path without logging out of a real tenant. | src/App.tsx; src/components/layout/Toolbar.tsx | Browser URL-state test | Verified | 2026-06-23 17:51 UTC | Browser route/exit: direct ?sampleTenant=1 opened sample workspace; Exit sample removed query and returned to sign-in screen with Sample tenant button. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-077 | Sample tenant | Deterministic sample Graph client | As a reviewer, I want sample data to exercise the same UI paths as Microsoft Graph so the demo proves the product workflow. | The sample Graph client implements overview, search, expansion, assignments, sign-in logs, user photos, app icons, and enlarged sample routes across users, groups, roles, devices, apps, policies, filters, scope tags, and Conditional Access data. Sample mode renders 81 objects / 37 relationships in the current default view. | src/demo/sampleTenantClient.ts; src/demo/sampleTenantData.ts; src/demo/sampleTenantClient.test.ts | Automated client contract plus browser walkthrough | Verified | 2026-06-24 04:03 UTC | Focused tests and Playwright sample smoke pass; browser sample mode shows 81 objects / 37 relationships and exercises users, devices, apps, policies, guardrails, sign-ins, CA data, app icons, and admin impact flows. | No | No fix needed | Not required; no issue found in this pass. | Updated after sample tenant expansion on codex/admin-impact-workflows.
TG-078 | Sample tenant | Real sample apps and icons | As a non-admin evaluator, I want recognizable real app icons so the sample graph looks credible and not like generic placeholders. | Sample apps are real apps with distinct icon data: Intune Company Portal, Microsoft Edge, Microsoft Defender, Windows App Mobile, SAP Concur, Microsoft Outlook, Microsoft Teams, Microsoft OneDrive, Zoom Workplace, Adobe Acrobat Reader, ServiceNow Agent, Salesforce, Slack, Microsoft Power BI, Microsoft Planner, and Microsoft Loop. Policy/configuration names must not appear as app nodes. | src/demo/sampleTenantData.ts; src/demo/sampleAppIcons.ts; src/demo/sampleTenantClient.test.ts | Automated sample catalog test plus visual smoke | Verified | 2026-06-24 04:03 UTC | Focused tests verify all real app labels, no policy-shaped app labels, and distinct image data URLs; generated SVG app tiles cover added real apps without fake product names. | No | No fix needed | Not required; no issue found in this pass. | Updated after sample app catalog expansion.
TG-079 | Sample tenant tutorial | Automatic sample guide and reopen | As a first-time user, I want guided onboarding in the sample tenant so I understand the major controls without admin knowledge. | The sample guide opens automatically in sample mode, can be dismissed, and can be reopened with the toolbar Guide button. The guide does not appear in live tenant mode. | src/components/demo/SampleTenantGuide.tsx; src/components/demo/sampleGuideSteps.ts; src/components/layout/AppShell.tsx; src/components/layout/Toolbar.tsx | Browser click-through test | Verified | 2026-06-23 17:51 UTC | Browser verifies guide opens automatically in sample mode and toolbar Guide remains available; guide is absent from normal sign-in after exit sample. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-080 | Sample tenant tutorial | Guide target highlight and auto-scroll | As a guided user, I want each tutorial step to focus the relevant UI region so I can follow along without hunting. | Every sample tutorial step with a referenced target scrolls that target into view before measuring the highlight; step 3 still scrolls the left sidebar to Object types. | src/components/demo/SampleTenantGuide.tsx; src/components/demo/sampleGuideSteps.ts; src/components/layout/Sidebar.tsx | Browser guide walkthrough plus focused guide-step invariant test | Retested passed | 2026-06-23 18:09 UTC | Playwright advanced all 8 guide steps and each referenced target was visible in the viewport; focused test enforces scrollBlock=center on every targeted step. | No | Fixed | Passed in TR-028 with zero browser console errors. | Updated after user requested tutorial scrolling for every referenced section.
TG-081 | Sample tenant tutorial | Guide polish and reduced motion | As a user sensitive to motion, I want onboarding animations to feel polished but optional. | Guide panel content enters with small staggered opacity/blur/translate motion, the close control has at least a 40px hit area, and prefers-reduced-motion disables the added animation. | src/styles/09-demo.css; src/components/demo/SampleTenantGuide.tsx | Visual smoke plus source check | Verified | 2026-06-23 17:51 UTC | Source/test verification covers guide motion, close hit target, reduced-motion CSS, and remounted step panel behavior; lint/typecheck pass. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-082 | Sign-in investigation | Conditional Access graph projection filter | As an investigator, I want to project only blocked or evaluated Conditional Access policies so the graph answers why access was denied or assessed. | The sign-in event detail has a Graph policies selector for All, Blocked, and Evaluated. Show on graph projects the event with policy nodes filtered according to that selector. | src/components/details/SignInInvestigation.tsx; src/graph/signInEventGraph.ts; src/components/layout/workspaceReducer.ts | Unit test plus browser sign-in projection test | Verified | 2026-06-23 17:51 UTC | Browser loaded sign-ins, selected blocked CA event, set Graph policies to Blocked, projected it; graph selected Failure / Azure Portal with blocking policy and excluded not-applied policy. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-083 | Workspace controls | Reset returns to original signed-in or sample user | As a user exploring the graph, I want Reset to return to the original tenant overview so I can recover from searches, projections, filters, or expansions. | Reset reloads overview state, clears transient graph/search/projection state, and resets the Three.js camera view. In sample mode it returns to the sample current user; in live mode it returns to the signed-in user overview. | src/components/layout/AppShell.tsx; src/components/layout/workspaceReducer.ts; src/components/graph/useTenantGraphRenderer.ts | Browser reset state test | Verified | 2026-06-23 17:51 UTC | Browser Reset after projection restored adele@contoso.example and original 25 object / 11 relationship graph; reducer test covers clearing search/filter/projection state. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-084 | Graph rendering | Fresh-load and reset illumination | As a graph user, I want objects to be visible when the graph first loads or resets so the map does not feel empty or muted. | Graph nodes receive short-lived additive illumination on first graph load, Reset View, and Reset Graph, then fade back to steady-state readability. | src/components/graph/useTenantGraphRenderer.ts; src/components/graph/tenantGraphSceneBuilder.ts; src/components/graph/threeGraphObjects.ts | Visual smoke plus graph object tests | Verified | 2026-06-23 17:51 UTC | Focused graph object test verifies reset illumination brightens and fully hides; source shows illumination triggered on fresh graph key and reset view. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-085 | Graph rendering | Enterprise cloud-map graph background | As an admin, I want a quiet topology-map background so graph data stays readable while the app feels premium. | The graph viewport uses a deep navy/black radial surface, subtle blueprint grid, cyan focus glow behind the selected area, and mild vignette without stars/noise/bright competing lines. | src/styles/06-graph-stage.css | Visual screenshot review | Verified | 2026-06-23 17:51 UTC | Browser graph canvas renders with zero errors; CSS source confirms deep navy radial surface, faint blueprint grid, focus glow, vignette, and no pseudo-element star/noise layer. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-086 | Graph rendering | Selected-node cue without cone spotlight | As a graph user, I want selected objects emphasized without a cone obscuring nearby graph data. | Selected nodes use rings, halos, and label emphasis; the tapered cone/cylinder spotlight is absent and covered by regression tests. | src/components/graph/threeGraphObjects.ts; src/components/graph/threeGraphObjects.test.ts | Automated geometry regression plus visual smoke | Verified | 2026-06-23 17:51 UTC | Focused test verifies selected anchor contains no ConeGeometry or CylinderGeometry; remaining ConeGeometry is edge direction marker, not selected spotlight. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-087 | Graph rendering | Renderer lifecycle split and cleanup | As a user navigating or signing out, I want the graph canvas to mount/unmount without leaked listeners or stale Three.js objects. | TenantGraphCanvas is a React shell; useTenantGraphRenderer owns Three.js setup, events, animation, resize, and disposal, and scene construction returns explicit pickables/animation objects for cleanup. | src/components/graph/TenantGraphCanvas.tsx; src/components/graph/useTenantGraphRenderer.ts; src/components/graph/tenantGraphSceneBuilder.ts | React Doctor plus source/test review | Verified | 2026-06-23 17:51 UTC | Source and typecheck verify TenantGraphCanvas delegates renderer lifecycle to useTenantGraphRenderer and scene construction to tenantGraphSceneBuilder with cleanup/disposal path. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-088 | Graph rendering | Object-type and app-image icons | As a non-admin viewer, I want nodes to look like their object family so I can understand the graph without reading every label. | Nodes use typed icons for users, devices, roles, groups, policies, filters, scope tags, cloud apps, sign-in events, and network locations; app/user nodes use hydrated image data when available and fall back to type icons. | src/components/graph/nodeIcons.ts; src/components/graph/useNodeImageCache.ts; src/graph/mediaEnrichment.ts; src/demo/sampleAppIcons.ts | Visual smoke plus media hydration tests | Verified | 2026-06-23 17:51 UTC | Browser legend/results expose typed icons and real app labels; focused tests verify app icon data URLs are distinct and use fallback-safe renderer paths. | No | No fix needed | Not required; no issue found in this pass. | Validated in TR-027 sample tenant browser pass plus focused tests.
TG-089 | Sample tenant | Large realistic sample tenant | As an evaluator, I want the sample tenant to feel like a real tenant so I can judge the product without connecting my environment. | Sample mode includes 19 users, 15 groups, 19 managed devices, 16 managed apps, directory roles, compliance/configuration/settings/enrollment policies, assignment filters, scope tags, detected apps, memberships, assignments, and Conditional Access sign-in events. The initial sample view renders 81 objects / 37 relationships. | src/demo/sampleTenantData.ts; src/demo/sampleTenantClient.ts; src/demo/sampleTenantClient.test.ts | Automated unit test and Playwright sample smoke | Verified | 2026-06-24 04:03 UTC | npx vitest sample tests pass; Playwright sample route reports 81 objects / 37 relationships, 17 people, 19 devices, 16 apps, 18 policies, and 11 guardrails. |  | No fix needed |  | Current sample tenant has enough variety for apps, groups, devices, policies, filters, roles, and sign-in investigation.
TG-090 | Admin investigation | Impact analyzer blast radius | As an Intune or Entra admin, I want a selected object blast-radius summary so I can understand what may be affected before making a change. | The sidebar shows Impact analyzer for a selected object and Tenant hygiene when no object is selected. It displays loaded counts for users, devices, groups, apps, policies, and filters derived from the graph neighborhood. | src/utils/adminInsights.ts; src/components/details/AdminImpactPanel.tsx; src/components/layout/workspaceSelectors.ts | Unit test and Playwright browser smoke | Verified | 2026-06-24 04:03 UTC | adminInsights unit tests pass; Playwright confirms Impact analyzer and blast-radius counts render in sample mode and update for Intune Company Portal selection. |  | No fix needed |  | Counts are intentionally scoped to loaded graph data, not guessed tenant totals.
TG-091 | Admin investigation | Risk and hygiene review signals | As an admin, I want obvious risky relationships surfaced so I can focus review time on broad or blocking changes. | The admin panel flags broad All users/All devices targets, required assignments, noncompliant devices, privileged role membership visibility, and unconnected apps/policies in the loaded graph with severity-coded findings. | src/utils/adminInsights.ts; src/utils/adminInsights.test.ts; src/components/details/AdminImpactPanel.tsx | Unit test and Playwright browser smoke | Verified | 2026-06-24 04:03 UTC | Unit tests cover broad target, required assignment, noncompliant device, and selected-object findings; Playwright shows Company Portal review signals for required broad target assignment. |  | No fix needed |  | Findings are static rows, not dead clickable controls.
TG-092 | Admin investigation | Recent change investigation hints | As an admin troubleshooting a change, I want recently changed related policies called out so I know where to inspect audit logs. | Nodes with recent created or modified metadata generate Recent changes entries that name the object, state whether it was created or modified, and advise checking audit logs before editing related assignments. | src/utils/adminInsights.ts; src/components/details/AdminImpactPanel.tsx | Unit test | Verified | 2026-06-24 04:03 UTC | adminInsights unit test creates a recently modified settings catalog policy and verifies Recent changes output. |  | No fix needed |  | Uses loaded Graph metadata only; live audit-log correlation remains a future extension.
TG-093 | Admin investigation | Copyable investigation evidence | As an admin, I want one-click evidence text so I can paste the investigation into a ticket or change record. | Copy evidence writes a concise text summary containing the selected subject, relationship count, blast radius, review findings, and recent change signals to the clipboard. | src/utils/adminInsights.ts; src/components/details/AdminImpactPanel.tsx | Unit test and Playwright browser smoke | Verified | 2026-06-24 04:03 UTC | investigationSummaryText unit test verifies summary content; Playwright clicked Copy evidence and observed Copied state. |  | No fix needed |  | Clipboard failure is caught so it does not block graph exploration.
TG-094 | Admin investigation | Saved investigation views | As an admin, I want to save a small set of investigation snapshots so I can return to important review contexts during a session. | Save view stores the current investigation summary in localStorage, caps saved entries at six, displays Saved investigations, and allows individual removal without affecting graph data. | src/components/details/AdminImpactPanel.tsx; src/styles/05-details.css | Playwright browser smoke | Verified | 2026-06-24 04:03 UTC | Playwright sample mode cleared localStorage, clicked Save view, confirmed Saved investigations appears and localStorage contains one saved investigation subject. |  | No fix needed |  | Saved views are local browser shortcuts, not tenant-shared records.
TG-095 | Mobile usability | Responsive workspace and touch navigation | As a mobile reviewer, I want the graph, results, filters, and access context reachable without layout overlap so I can inspect a sample tenant from a phone. | At <=980px the shell uses natural toolbar height, shows a sticky four-button workspace nav, keeps the graph first, caps the relationship inspector, stacks dense filters, and clamps tutorial highlights inside the viewport. | src/components/layout/AppShell.tsx; src/components/layout/Toolbar.tsx; src/styles/03-toolbar.css; src/styles/07-responsive.css; src/components/demo/SampleTenantGuide.tsx | Browser smoke and static verification | Verified | 2026-06-24 04:39 UTC | Mobile smoke passed at 320px, 390px, and 430px with no horizontal overflow; Results jump lands below sticky nav; desktop 1440px keeps original toolbar and hides mobile nav. |  | No fix needed |  | No separate npm typecheck script exists; direct npx tsc -b and npm run build both passed.

## Test Runs
Run ID | Date | Scope | Command or Method | Result | Evidence | Notes
TR-001 | 2026-06-21 20:47 UTC | Automated quality gates | npm run lint; npm run test; npm run build; npm audit --audit-level=high | Pass | Shell output from current audit loop | 29 unit tests passed; build passed with existing large chunk warning; audit found 0 high vulnerabilities.
TR-002 | 2026-06-21 20:47 UTC | Static source scans | rg reduced motion, aria/roles, TODO/debugger/console | Pass | src/styles/07-responsive.css and rg scan output | Reduced motion fallback present; no TODO/FIXME/debugger/console logging in src.
TR-003 | 2026-06-21 20:47 UTC | MSAL sign-in click | Playwright click on stale anonymous Sign In tab | Pass | Popup opened with auth code and tab became workspace | Confirms earlier nested-prompt popup issue is not reproducing.
TR-004 | 2026-06-21 20:47 UTC | Desktop graph smoke | Playwright viewport 1440x1000 plus screenshot | Pass | tasks/browser-smoke/desktop-authenticated.png | Canvas, cluster zones, typed legend, minimap, inspector, and selected node visible.
TR-005 | 2026-06-21 20:47 UTC | Search/results/selection smoke | Playwright search iOS, load more, select result | Pass | Browser interaction output | Load more 30->60; iOS search returned five relevant rows; details pinned selected object.
TR-006 | 2026-06-21 20:47 UTC | Sign-in logs and Conditional Access | Playwright load logs for Break Glass user | Pass | Live sign-in panel output | 25 events, one failure, report-only CA counts returned.
TR-007 | 2026-06-21 20:47 UTC | Sign-in detail projection | Playwright event click and Project onto graph | Pass | Browser interaction output | Sign-in detail opened; projection increased graph objects and reset removed projection after proper wait.
TR-008 | 2026-06-21 20:47 UTC | Empty/filter/reset behavior | Playwright filter all object types off/on and strict reset wait | Pass | Browser interaction output | Explicit empty state shown at 0 objects/0 relationships; reset restored overview.
TR-009 | 2026-06-21 20:47 UTC | Mobile responsive smoke | Playwright viewport 390x844 plus screenshot | Pass | tasks/browser-smoke/mobile-authenticated.png | No horizontal overflow; toolbar, graph, legend, minimap fit within 390px.
TR-010 | 2026-06-21 20:51 UTC | Graph hover/edge/cluster live interactions | Playwright coordinate sweep and canvas clicks | Pass | Browser interaction output | Node tooltip, edge inspector selection, and Policies cluster isolation verified.
TR-011 | 2026-06-21 20:51 UTC | Sign-out flow | Playwright account menu Sign out and Microsoft account-picker confirmation | Pass | Browser interaction output | Sign-out returned to Tenant Graph sign-in screen; re-auth popup opened and is awaiting user completion.
TR-012 | 2026-06-21 20:55 UTC | Canceled MSAL popup UX | Playwright click Sign In, close popup, inspect alert | Pass | Browser interaction output | Before fix no auth-error rendered; after fix role=alert shows cancellation message and Sign in remains available.
TR-013 | 2026-06-21 21:05 UTC | Remote result filter regression | Live browser iOS search, all object types off/on | Pass | Browser interaction output | Before fix stale iOS rows remained; after fix filtered results are empty with No matches.
TR-014 | 2026-06-21 21:05 UTC | Keyboard-only workspace tour | Playwright keyboard Tab/Enter sequence | Pass | Browser interaction output | Tab starts at search; Enter submits search; Tab reaches result; Enter selects and pins details.
TR-015 | 2026-06-21 21:05 UTC | Relationship filters and external links | Browser checkbox toggle plus window.open interception | Pass | Browser interaction output | Scope tag relationship filter changes relationship count; account/admin links open expected URLs.
TR-016 | 2026-06-21 21:05 UTC | Admin/readable detail surfaces | Browser Admin mode and Friendly Names disclosure checks | Pass | Browser interaction output | Evidence drawer, raw Graph IDs, and technical details disclosure verified.
TR-017 | 2026-06-21 21:06 UTC | Graph direct interaction pass | Playwright node-coordinate click, wheel, drag, shifted drag, focus-depth select changes | Pass | Browser interaction output | Direct node click selected details; zoom/pan/rotate kept canvas usable; focus depth Off/Direct/Two-Hop values applied.
TR-018 | 2026-06-21 21:12 UTC | Forced warning/path/load-more unit coverage | Vitest graphCalls, readable path, and sign-in nextLink tests | Pass | npm run test output: 4 files, 34 tests | Graph warning aggregation, permissionError propagation, readable path positive case, and sign-in nextLink load-more behavior covered.
TR-019 | 2026-06-21 21:13 UTC | Media fallback and sign-in permission forced-state tests | Vitest media enrichment tests plus useSignInInvestigation GraphError test | Pass | npm run test output: 5 files, 35 tests | Profile photo/app icon fallbacks and sign-in permission guidance are covered without needing live tenant failures.
TR-020 | 2026-06-21 21:16 UTC | Final source-only row closure | Vitest auth config, DetailsPanel no-selection, visual policy, label collision tests plus source/browser evidence | Pass | npm run test output: 9 files, 41 tests | Missing config, no-selection prompt, relationship visual styles, label collision, and lifecycle evidence completed.
TR-021 | 2026-06-21 21:17 UTC | Final post-fix browser smoke | Playwright reload, overview, remote search plus filters, keyboard result selection, graph canvas visibility | Pass | Browser interaction output | Post-fix app smoke passed: 176 objects/96 relationships, iOS search 5 rows, all object types off gives 0 rows, keyboard selection pins details, canvas visible.
TR-022 | 2026-06-21 23:48 UTC | Conditional Access failure projection focus | npm run test -- src/components/layout/useTenantGraphWorkspace.test.ts src/graph/signInLogs.test.ts | Pass | Vitest output: 2 files, 12 tests | Jorge Suarez failure projection regression passed; failed event remains selected/centered after an earlier success projection.
TR-023 | 2026-06-21 23:48 UTC | Jorge Suarez CA failure live workflow | Playwright live browser: select Jorge, project success, switch CA Failed + Result Failure, project failed event | Pass | Browser interaction output | Success projection changed graph selection to Success / Tenant Graph; projected context still loaded 5 Jorge failures; failed projection selected Failure / Tenant Graph.
TR-024 | 2026-06-22 00:24 UTC | Full post-fix feature-story regression sweep | npm run lint; npm run test; npm run build; npm audit --audit-level=high; Playwright live browser sweep | Pass | Shell and Playwright output from current goal loop | All 74 workbook stories are Verified or Retested passed. Live sweep covered overview, search, filters, reset, Jorge Suarez sign-ins, success projection, CA Failed + Result Failure, blocked failed projection, and mobile layout. No user-facing Graph warnings rendered on the verified path; console-only photo 404 fallback and one transient external Graph 429 were non-blocking.
TR-026 | 2026-06-23 17:40 UTC | Feature inventory | Static source inventory plus canonical spreadsheet update | In progress | Current worktree inspection and workbook regeneration | Added TG-075 through TG-088 for sample tenant, tutorial, real sample app icons, CA graph projection filter, reset illumination, graph background, and renderer lifecycle. Full user-story testing loop is next.
TR-027 | 2026-06-23 17:51 UTC | TG-075..TG-088 | Sample tenant browser + focused tests | npx tsc -b --pretty false; npm run lint; npx vitest run src/demo/sampleTenantClient.test.ts src/components/graph/threeGraphObjects.test.ts src/components/graph/graphVisualPolicy.test.ts src/components/layout/useTenantGraphWorkspace.test.ts; Playwright sample route smoke | Passed | 0 browser console errors; one known Three.js/Vanta warning; no new UX/logistical errors found.
TR-028 | 2026-06-23 18:09 UTC | TG-080 | Tutorial target auto-scroll retest | npx vitest run src/demo/sampleTenantClient.test.ts; npx tsc -b --pretty false; npm run lint; npm run test; npm run build; npm audit --audit-level=high; git diff --check; Playwright sample guide all-step probe | Passed | All eight tutorial targets were visible after their guide step activated; zero browser console errors.
TR-029 | 2026-06-24 04:03 UTC | TG-077..TG-094 admin impact and sample expansion | npx tsc -b --pretty false; npm run lint; npm run test; npm run build; npm audit --audit-level=high; Playwright sample route smoke; vercel --yes; vercel curl /?sampleTenant=1 | Passed | 68 tests passed; lint/typecheck/build/audit passed; Playwright confirmed 81 objects / 37 relationships, Impact analyzer, broad-target review signals, Copy evidence, and Save view; Vercel preview returned app HTML. | Vite still reports the existing large chunk warning. Dev browser still reports the known duplicate Three.js warning from Vanta plus app Three.js in local development; no app console errors.
TR-030 | 2026-06-24 04:39 UTC | TG-095 mobile optimization | npm run lint; npx tsc -b; npm run test; npm run build; Playwright browser smoke at 320, 390, 430, and 1440 widths | Passed | Lint passed; TypeScript compiled; 68 tests passed; production build passed; browser smoke found no toolbar/workspace overlap or horizontal overflow after tutorial overlay clamp. | Build still reports the existing large chunk warning.
TR-031 | 2026-06-24 04:52 UTC | Thermo-nuclear QA loop and React Doctor remediation | npm run lint; npx react-doctor@latest --verbose --scope changed; npm run doctor -- --verbose; npx tsc -b; npm run test; npm run build; git diff --check | Passed | React Doctor improved from 91/100 with two js-hoist-intl warnings to 100/100 with no issues; lint/typecheck/tests/build passed; strict review fixes applied to admin-impact graph scoping and copy-evidence timer lifecycle. | Build still reports the existing Vite large-chunk warning; not a lint, React Doctor, or thermo-review blocker.

## Errors
Error ID | Feature ID | Severity | Type | Observed Behavior | Expected Behavior | Evidence | Fix | Status | Retest Evidence
ERR-001 | TG-025 | Low | External optional media 404 | Microsoft Graph returns 404 for a user 48x48 profile photo and Chrome records it as a failed resource. | Missing profile photos should fall back to the user glyph without blocking graph load or showing user-facing warnings. | .playwright-mcp/console-2026-06-21T20-33-13-216Z.log | No product fix; fallback behavior is working and no user-facing warning appears. | No fix needed | Observed repeatedly during reset/sign-in tests; app remained functional.
ERR-002 | TG-041 | Low | Test harness false positive | Initial smoke expected an exact button named Expand while selected objects correctly showed No expansion or Expanded depth 1 disabled states. | Automation should account for disabled completed/no-expansion action labels. | Browser interaction output from 2026-06-21 live pass | No product fix; rerun verified visible disabled/guidance states. | No fix needed | Retest passed through details-panel control inspection.
ERR-003 | TG-014 | Low | Test harness stale read | Initial reset script read object counts before the async reload finished, making projected sign-in nodes appear persistent. | Reset should be evaluated after loading state clears. | Browser interaction output from strict reset wait | No product fix; strict wait confirmed reset returns to 176 objects / 96 relationships. | No fix needed | Retest passed with loading-state wait.
ERR-004 | TG-004 | Medium | UX silence on canceled auth popup | Closing the Microsoft sign-in popup returned to the sign-in screen without visible feedback. | Canceled sign-in should explain what happened and leave an obvious retry action. | Playwright canceled-popup retest | Added typed signInErrorMessage helper and rendered cancellation text in SignInScreen. | Fixed | Retest passed with visible role=alert cancellation message.
ERR-005 | TG-020 | Medium | Stale remote search results after object-type filters changed | After searching iOS, turning every object type off showed 0 graph objects but still listed the previous five iOS remote search results. | Object-type filters should apply to current remote search results as well as graph objects/local results. | Browser reproduction: iOS search then all object types off | Added filterNodesByVisibleTypes and applied it to remoteResults in useTenantGraphWorkspace; added unit regression coverage. | Fixed | Retest passed: filteredResultCount=0 and Results shows No matches.
ERR-006 | TG-073 | High | Wrong graph focus for failed sign-in projection | When a successful sign-in projection already existed, showing a failed sign-in on the graph could select the older successful sign-in node because the reducer picked the first signInEvent in the merged graph. | The graph should select and center the exact sign-in event the user clicked, including failed events for Jorge Suarez. | Code audit plus reducer regression in useTenantGraphWorkspace.test.ts | Exported signInEventNodeId and used it in projectSignInEvent to select signInEvent:<clicked event id>. | Fixed
ERR-007 | TG-074 | High | Projected sign-in context trapped follow-up filters | After projecting a successful sign-in, the selected object became that sign-in event. Switching filters to CA Failed and Result Failure then searched the success event context and returned no failures. | From a projected sign-in, follow-up sign-in filters should stay scoped to the event user so Jorge Suarez failures can be loaded and projected without reselecting the user. | Live browser retest plus signInLogQuery regression tests | Added user metadata to projected sign-in nodes and made sign-in event contexts query/filter by that user before falling back to event ID. | Fixed

## Summary
Canonical tracker | tasks/tenant-graph-feature-stories.xlsx
Created | 2026-06-21 20:32 UTC
Last inventory update | 2026-06-24 04:39 UTC
Last verification update | 2026-06-24 04:52 UTC
Source of truth | Current worktree under /Users/jorgeasaurus/Code/TenantGraph
Feature rows | 95
Current phase | Thermo-nuclear QA loop, lint, and React Doctor are verified clean; mobile, admin impact, and sample tenant work remain verified.
Canonical sheets | Feature Stories; Test Runs; Errors; Summary
Status vocabulary | Needs test; Verified; Retested passed; Error found; Fix pending; No fix needed
Duplicate workbook note | Removed duplicate workbook; this is the only tracker workbook under tasks/.